PMBOK Chapter 10    (Project Communications Management)

Study Notes Submitted by Jesse Steele

Project Communications Management includes the processes required to ensure timely and appropriate generation, collection, dissemination, storage, and ultimate disposition of project information. It provides the critical links among people, ideas, and information that are necessary for success.

10.1 Communications Planning—determining the information and communications needs of the stakeholders: who needs what information, when will they need it, and how will it be given to them.

10.2 Information Distribution—making needed information available to project stakeholders in a timely manner.

10.3 Performance Reporting—collecting and disseminating performance information.    This includes status reporting, progress measurement, and forecasting.

10.4 Administrative Closure—generating, gathering, and disseminating information to formalize phase or project completion. These processes interact with each other and with the processes in the other knowledge areas as well. Each process may involve effort from one or more individuals or groups of individuals based on the needs of the project. Each process generally occurs at least once in every project phase.

10.1 COMMUNICATIONS PLANNING

Communications planning involves determining the information and communications needs of the stakeholders: who needs what information, when will they need it, and how will it be given to them. On most projects, the majority of communications planning is done as part of the earliest project phases. However, the results of this process should be reviewed regularly throughout the project and revised as needed to ensure continued applicability.    Communications planning is often tightly linked with organizational planning (described in Section 9.1) since the project’s organizational structure will have a major effect on the project’s communications requirements.

10.1.1 Inputs to Communications Planning

.1 Communications requirements. Communications requirements are the sum of the information requirements of the project stakeholders. Requirements are defined by combining the type and format of information required with an analysis of the value of that information. Project resources should be expended only on communicating information which contributes to success or where lack of communication can lead to failure. Information typically required to determine project communications requirements includes:

• Project organization and stakeholder responsibility relationships.

• Disciplines, departments, and specialties involved in the project.

• Logistics of how many individuals will be involved with the project and at which locations.

• External information needs (e.g., communicating with the media).

.2 Communications technology. The technologies or methods used to transfer information back and forth among project elements can vary significantly: from brief conversations to extended meetings, from simple written documents to immediately accessible on-line schedules and databases. Communications technology factors which may affect the project include:

- The immediacy of the need for information—is project success dependent upon having frequently updated information available on a moment’s notice, or would regularly issued written reports suffice?

- The availability of technology—are the systems that are already in place appropriate, or do project needs warrant change?

- The expected project staffing—are the communications systems proposed compatible with the experience and expertise of the project participants, or will extensive training and learning be required?

- The length of the project—is the available technology likely to change before the project is over in a manner that would warrant adopting the newer technology?

.3 Constraints. Constraints are factors that will limit the project management team’s options. For example, if substantial project resources will be procured, more consideration will need to be given to handling contract information.

.4 Assumptions. Assumptions are factors that, for planning purposes, will be considered to be true, real, or certain. Assumptions generally involve a degree of risk.

- Tools and Techniques for Communications Planning

.1 Stakeholder analysis. The information needs of the various stakeholders should be analyzed to develop a methodical and logical view of their information needs and sources to meet those needs

.

- Outputs from Communications Planning

.1 Communications management plan. A communications management plan is a document which provides:

• A collection and filing structure which details what methods will be used to gather and

store various types of information.

• A distribution structure which details to whom information (status reports, data, schedule,

technical documentation, etc.) will flow, and what methods (written reports, meetings, etc.)

will be used to distribute various types of in-formation.

• A description of the information to be distributed, including format, content, level of detail,

and conventions/definitions to be used.

• Production schedules showing when each type of communication will be produced.

• Methods for accessing information between scheduled communications.

• A method for updating and refining the communications management plan as the project

progresses and develops.

10.2 INFORMATION DISTRIBUTION

Information distribution involves making needed information available to project stakeholders in a timely manner. It includes implementing the communications management plan as well as responding to unexpected requests for information.

10.2.1 Inputs to Information Distribution

.1 Work results. Work results are described in Section 4.2.3.1.

.2 Communications management plan. The communications management plan is described in

Section 10.1.3.1.

.3 Project plan. The project plan is described in Section 4.1.3.1.

10.2.2 Tools and Techniques for Information Distribution

.1 Communications skills. Communications skills are used to exchange information. The sender is responsible for making the information clear, unambiguous, and complete so that the receiver can receive it correctly and for confirming that it is properly understood. The receiver is responsible for making sure that the information is received in its entirety and understood correctly. Communicating has many dimensions:

• Written and oral, listening and speaking.

• Internal (within the project) and external (to the customer, the media, the public, etc.).

• Formal (reports, briefings, etc.) and informal (memos, ad hoc conversations, etc.).

• Vertical (up and down the organization) and horizontal (with peers).

.2 Information retrieval systems. Information can be shared by team members through a variety of methods including manual filing systems, electronic text data-bases, project management software, and systems which allow access to technical documentation such as engineering drawings.

.3 Information distribution systems. Project information may be distributed using a variety of methods including project meetings, hard copy document distribution, shared access to networked electronic databases, fax, electronic mail, voice mail, and video conferencing.

- Outputs from Information Distribution

.1 Project records. Project records may include correspondence, memos, reports, and documents describing the project.

10.3 PERFORMANCE REPORTING

Performance reporting involves collecting and disseminating performance information in order to provide stakeholders with information about how resources are being used to achieve project objectives. This process includes:

• Status reporting—describing where the project now stands.

• Progress reporting—describing what the project team has accomplished.

• Forecasting—predicting future project status and progress.

Performance reporting should generally provide information on scope, schedule, cost, and quality. Many projects also require information on risk and procurement.

- Inputs to Performance Reporting

.1 Project plan. The project plan is discussed in Section 4.1.3.1. The project plan contains the various baselines that will be used to assess project performance.

.2 Work results. Work results—which deliverables have been fully or partially completed, what costs have been incurred or committed, etc.—are an output of project plan execution.

.3 Other project records. Project records are discussed in Section 10.2.3.1.

- Tools and Techniques for Performance Reporting

.1 Performance reviews. Performance reviews are meetings held to assess project status or progress. Performance reviews are typically used in conjunction with one or more of the performance reporting techniques described below.

.2 Variance analysis. Variance analysis involves comparing actual project results to planned or expected results. Cost and schedule variances are the most frequently analyzed, but variances from plan in the areas of scope, quality, and risk are often of equal or greater importance.

.3 Trend analysis. Trend analysis involves examining project results over time to determine if performance is improving or deteriorating.

.4 Earned value analysis. Earned value analysis in its various forms is the most commonly used method of performance measurement. It integrates scope, cost, and schedule measures to help the project management team assess project performance.

Earned value involves calculating three key values for each activity:

• The budget, also called the budgeted cost of work scheduled (BCWS), is that portion of

the approved cost estimate planned to be spent on the activity during a given period.

• The actual cost, also called the actual cost of work performed (ACWP), is the total of direct

and indirect costs incurred in accomplishing work on the activity during a given period.

• The earned value, also called the budgeted cost of work performed (BCWP), is a percentage

of the total budget equal to the percentage of the work actually completed. Many earned value

implementations use only a few percentages (e.g., 30 percent, 70 percent, 90 percent, 100

percent) to simplify data collection. Some earned value implementations use only 0 percent or

100 percent (done or not done) to help ensure objective measurement of performance.

These three values are used in combination to provide measures of whether or not work is being accomplished as planned. The most commonly used measures are the cost variance (CV = BCWP – ACWP), the schedule variance (SV = BCWP – BCWS), and the cost performance index (CPI = BCWP / ACWP). The cumulative CPI (the sum of all individual BCWPs divided by the sum of all individual ACWPs) is widely used to forecast project cost at completion. In some application areas, the schedule performance index (SPI = BCWP / BCWS) is used to forecast the project completion date.

.5 Information distribution tools and techniques. Performance reports are distributed using the tools and techniques described in Section 10.2.2.

- Outputs from Performance Reporting

.1 Performance reports. Performance reports organize and summarize the information gathered and present the results of any analysis.    Common formats for performance reports include bar charts (also called Gantt charts), S-curves, histograms, and tables.

.2 Change requests. Analysis of project performance often generates a request for a change to some aspect of the project. These change requests are handled as de-scribed in the various change control processes (e.g., scope change management, schedule control, etc.).

10.4 ADMINISTRATIVE CLOSURE

The project or phase, after either achieving its objectives or being terminated for other reasons, requires closure. Administrative closure consists of verifying and documenting project results to formalize acceptance of the product of the project by the sponsor, client, or customer. It includes collection of project records, ensuring that they reflect final specifications, analysis of project success and effectiveness, and archiving such information for future use.

- Inputs to Administrative Closure

.1 Performance measurement documentation. All documentation produced to record and analyze project performance, including the planning documents which established the framework for performance measurement, must be available for review during administrative closure.

.2 Documentation of the product of the project. Documents produced to describe the product of the project (plans, specifications, technical documentation, drawings, electronic files, etc.—the terminology varies by application area) must also be available for review during administrative closure.

.3 Other project records. Project records are discussed in Section 10.2.3.1.

- Tools and Techniques for Administrative Closure

.1 Performance reporting tools and techniques. Performance reporting tools and techniques are discussed in Section 10.3.2.

- Outputs from Administrative Closure

.1 Project archives. A complete set of indexed project records should be prepared for archiving by the appropriate parties. Any project-specific or program-wide historical databases pertinent to the project should be updated. When projects are done under contract or when they involve significant procurement, particular attention must be paid to archiving of financial records.

.2 Formal acceptance. Documentation that the client or sponsor has accepted the product of the project (or phase) should be prepared and distributed.

.3 Lessons learned. Lessons learned are discussed in Section 4.3.3.3.